## Sheet1
RAID (Risks, Assumptions, Issues, Dependencies) Log
Project: | Teaching CST2234
Project Manager | Jason Abt
Project start date: | 2023-09-07
| ID | Status | Raised By | Date Raised | Type | Name | Description | Probability | Impact | Actions / Mitigation Plan | Owner | Decision | Decision Date
| 1 | Closed | Jenn | 2023-09-09 | Risk | Getting lost | Jason could get lost on his way to the classroom on his first day | High | Would miss first lecture | Study map and find room day before class | Jason | Mitigate risk | 2023-09-10
| 2 | Open | Ali | 2023-09-13 | Issue | Dry erase markers | No dry erase markers in classroom | High | Course content not delivered as well | Get new markers from office | Jason | Resolve issue | 2023-09-14
| 3 | Closed | Yu | 2023-09-14 | Risk | Power outage | Power could go out in classroom during storm | Low | May not be able to deliver lecture | Buy a generator for the classroom | Jason | Accept risk | 2023-09-15
| 4 | Open | Jacob | 2023-09-20 | Issue | No coffee | Jason can't get his coffee because Starbucks will be closed next week | High | Jason will fall asleep during class, lecture not delivered | Show Jason where to find another Starbucks | Jacob | Resolve issue | 2023-09-20